## Test_Summary
Field | Value
Project | Sanitized Well Operations QA Portfolio
Test Cycle | Cycle 1 - Functional + Regression
Environment | QA / Demo Environment
Scope | Authentication, Dashboard, Well Management, Well Information, Wellbore, Engineering, Treatment, MiniFrac/DFIT, Version Management
Planned Test Cases | 132
Executed Test Cases | 132
Initial Passed | 122
Initial Failed | 10
Blocked | 0
Initial Pass Rate | 92.42%
Defects Logged | 10
Defects Retested | 10
Retest Passed | 10
Final Passed | 132
Final Failed | 0
Final Pass Rate | 100%
Regression Cases | 15
Regression Passed | 15
Regression Failed | 0
Regression Pass Rate | 100%
Final Assessment | All planned cases executed; initial failures were retested after fixes; regression suite passed.

## Module_Summary
Module | Planned | Executed | Initial Passed | Initial Failed | Retest Passed | Final Passed | Final Failed | Status
Login | 15 | 15 | 15 | 0 | 0 | 15 | 0 | Passed
Dashboard | 12 | 12 | 12 | 0 | 0 | 12 | 0 | Passed
Well Management | 15 | 15 | 13 | 2 | 2 | 15 | 0 | Passed
Well Information | 15 | 15 | 13 | 2 | 2 | 15 | 0 | Passed
Wellbore Configuration | 15 | 15 | 14 | 1 | 1 | 15 | 0 | Passed
Engineering Parameters | 15 | 15 | 14 | 1 | 1 | 15 | 0 | Passed
Treatment | 15 | 15 | 14 | 1 | 1 | 15 | 0 | Passed
MiniFrac DFIT | 15 | 15 | 13 | 2 | 2 | 15 | 0 | Passed
Version Management | 15 | 15 | 14 | 1 | 1 | 15 | 0 | Passed

## Defect_Closure
Defect ID | Module | Severity | Priority | Initial State | Fix Verification | Retest | Regression Impact | Final Status
BUG-001 | Well Management | High | High | Failed | Search behavior corrected | Passed | Well search/filter | Closed
BUG-002 | Well Management | High | High | Failed | Status refresh corrected | Passed | Well status | Closed
BUG-003 | Well Information | High | High | Failed | Persistence corrected | Passed | Well information | Closed
BUG-004 | Wellbore Configuration | High | High | Failed | Sequence validation corrected | Passed | Wellbore validation | Closed
BUG-005 | Engineering Parameters | High | Critical | Failed | Recalculation corrected | Passed | Engineering results | Closed
BUG-006 | Treatment | High | High | Failed | Totals recalculation corrected | Passed | Treatment totals | Closed
BUG-007 | MiniFrac DFIT | High | Critical | Failed | Clean Volume calculation corrected | Passed | DFIT calculations | Closed
BUG-008 | Version Management | Critical | Critical | Failed | Context isolation corrected | Passed | Version integrity | Closed
BUG-009 | RBAC | Critical | Critical | Failed | Unauthorized action blocked | Passed | RBAC regression | Closed
BUG-010 | Well Information | Medium | Medium | Failed | Required field validation corrected | Passed | Validation | Closed

## Sign_Off
Area | Status | Owner | Date | Comments
Test Planning | Completed | QA | 2026-09-23 | Scope, strategy and test data prepared
Functional Execution | Completed | QA | 2026-09-23 | 132/132 test cases executed
Defect Retest | Completed | QA | 2026-09-23 | 10/10 defects retested successfully
Regression | Completed | QA | 2026-09-23 | 15/15 regression cases passed
RTM | In Progress | QA | 2026-09-23 | Core scope covered; extended modules marked pending
Final QA Assessment | Completed | QA | 2026-09-23 | Final execution and regression results recorded